## Sheet1
Projektets Navn | MotorHome
Projekt deltager | Ali Raza | Umit Arabaci | Omar Atik | Edmund Bidjeck
Startsdato | Tirsdag | 2020-05-12
Deadline | Torsdag | 2020-06-04
Opgaver | Ansvar | Start | slut | Dage | Status | 2020-05-12 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-16 | 2020-05-16 | 2020-05-17 | 2020-05-18 | 2020-05-19 | 2020-05-20 | 2020-05-21 | 2020-05-20 | 2020-05-21 | 2020-05-22 | 2020-05-23 | 2020-05-24 | 2020-05-25 | 2020-05-26 | 2020-05-27 | 2020-05-28 | 2020-05-29 | 2020-05-30 | 2020-05-31 | 2020-06-01 | 2020-06-02 | 2020-06-03 | 2020-06-04
2020-04-14 | Alle | 2020-05-12 | 2020-05-12 | 1 | Complete
Første Møde | Alle | 2020-05-12 | 2020-05-12 | 0 | Complete
Defineret kravene | Alle | 2020-05-12 | 2020-05-14 | 2 | Complete
Inception
Iteration 1
Risikoanalyse og plan | Umit | 2020-05-13 | 2020-05-14 | 1 | Complete
Feasibility study | Ali Raza | 2020-05-13 | 2020-05-14 | 1 | Complete
SWOT analyse | Omar | 2020-05-13 | 2020-05-14 | 1 | Complete
Stakeholders | Edmond | 2020-05-13 | 2020-05-14 | 1 | Complete
Faceplan for Inception | Umit | 2020-05-13 | 2020-05-14 | 1 | Complete
Elaboration
Iteration 1
Supplementary specification | Ali & Edmond | 2020-05-13 | 2020-05-14 | 1 | Complete
Use case Breif | Omar | 2020-05-13 | 2020-05-14 | 1 | Complete
Use case casual | Omar | 2020-05-13 | 2020-05-14 | 1 | Complete
Use Case Fully Dressed | Omar | 2020-05-13 | 2020-05-14 | 1 | Complete
Use Cases | Omar | 2020-05-14 | 2020-05-16 | 2 | Complete
Iteration 2
Domain Model | Ali & Umit | 2020-05-15 | 2020-05-16 | 1 | Complete
SSD 1 & SSD 2 | Ali & Umit | 2020-05-15 | 2020-05-16 | 1 | Complete
SD | Ali & Umit | 2020-05-15 | 2020-05-16 | 1 | Complete
Conceptuel model | Ali & Umit | 2020-05-15 | 2020-05-19 | 4 | Complete
Grasp | Edmond | 2020-05-15 | 2020-05-16 | 1 | Complete
Class Diagram based on Conceptuel | Ali & Umit | 2020-05-15 | 2020-05-16 | 1 | Complete
Eer Diagram | Ali & Umit | 2020-05-17 | 2020-05-18 | 1 | Complete
Iteration 3
Normalisering | Ali & Umit | 2020-05-18 | 2020-05-22 | 4 | Complete
Phase plan for Elaboration | Umit | 2020-05-22 | 2020-05-23 | 1 | Complete
Planing for next phase | Alle | 2020-05-22 | 2020-05-22 | 0 | Complete
Construction
Iteration 1
GearHost & Database ready | Umit & Omar | 2020-05-20 | 2020-05-24 | -4 | Complete
MySQL Script & All tables | Umit & Omar | 2020-05-22 | 2020-05-24 | 2 | Complete
InteliJ & Spring & Meaven ON | Umit & Omar | 2020-05-23 | 2020-05-25 | 2 | Complete
UML description & diagrams and updates | Umit & Ali | 2020-05-24 | 2020-05-26 | 2 | Complete
Iteration 2
Architecture Layers | Alle | 2020-05-27 | 2020-06-01 | 5 | Complete
HTML & CSS | Alle | 2020-05-27 | 2020-05-31 | 4 | Complete
Web Design | Alle | 2020-05-27 | 2020-06-01 | 5 | Complete
Collect the code for a finished program | Alle | 2020-06-01 | 2020-06-02 | 1 | Complete
Phase plan for Construction | Umit | 2020-06-02 | 2020-06-02 | 1 | Complete
Planing for next phase | Alle | 2020-06-02 | 2020-06-02 | 0 | Complete
Transition
Class Diagram based on Final Code | Umit | 2020-06-02 | 2020-06-02 | 0 | Complete
Ready-Made Report | Omar | 2020-06-02 | 2020-06-02 | 0 | Complete
Ready-Made Faceplan | Umit | 2020-06-02 | 2020-06-04 | 2 | Complete
jUnit Tests | Ali | 2020-06-01 | 2020-06-04 | 3 | Complete
Comment on special conditions | Alle | 2020-06-01 | 2020-06-04 | 3 | Complete
Solutions that require special arguments | Ali | 2020-06-01 | 2020-06-04 | 3 | Complete
Finished Project | Alle | 2020-06-01 | 2020-06-04 | 3 | Complete